## Sheet1
SECTION | FUNCTIONALITY | UI | Expected Completion Date | Completed Tasks
Home Landing page | The key features are present | Can the page be made a bit more minimalistic | 24/01/2022 | Completed but not yet received feedback
| Can we add a footer | Can the fonts and colours be adjusted to be more legible
| The “Discover more” and “view more” links are leading to nowhere, please address this | The buttons having grey makes them and the page dull
| The three buttons are confusing can we change them to become; | Can the text layout on the sections that describe what lay links is be changed to make it pop some more and perhaps add an image for each section on the homepage
Find a minister
Enroll as a minister
Enroll a ministry
Membership enrollment | Could we change that to simply “Invite a minister” |  |  | Completed changing that button
Membership and ministry Sign up/enrollment | Could we have a brief explainer of the process and requirements at the top of the signup page |  | 28/1/2022 | saya.jackson@gmail.com
| Can we have a progress tracker so one knows where they are, how much is remaining and can also go back and forward as the need arises when filling out the form fields. |  | The request for the list of conferences I need either an excel sheet, csv, api containing that list,
|  |  | Or a website containing such a list so that I can scrape it off that data. | Tasks Completed by
| Can we add a confirm password field in the sign up |  |  | 28/1/2022
| Can we have a drop-down with options for the conference name |  |  | 1. Task of Progress tracker
2. Added confirm password field
| Can the option be conference/field so that we do not have separate fields for that |  |  | 3. Separation of fields
4. Created Referees table at the backend but not yet linked.
| Can we have a drop-down with options for the host church name |  |  | 5. Added social authentication .
On location of the church can we have a drop-down
For the phone numbers, can we have the option to select country so that we have a country code set first
Instead of position in the church, can we have a drop-down on the various lay ministry caress we are signing people up for and an “other” option for people who wish to specify an uncaptured option
Can we have the option to sign up with social media/google and then fill the remaining details manually
When I click register, nothing happens.
My hope was that I receive a confirmation message explaining the next steps and directing me to the platform some more
Also I was hoping a message would be sent to my referee asking them to offer additional information about me.
Can we give both email and phone numbers for referees?
After signing up, the ministers can continue to build their profile, add media they have and manage their calendar. Please provide for these functionalities
Speaker request | The form it is hoped would state things like |  | 2022-01-02
-The event
- The requesting church
- The date(s)
-The venue
- The theme
- The speaker requested
- Travel and accommodation details
We sent you a sample form for this, please have a look
Blog | Consider adding | A mock-up of blogs on the page would help with visualising | 2022-03-02
- Topic classifications
- Author classifications
- Trending
- Featured
Course | No feedback possible, the page is blank | No feedback possible, the page is blank | FEED DATA
Shop | No feedback possible, the page is blank | No feedback possible, the page is blank | FEED DATA
Ministers | No feedback possible, the page is blank | No feedback possible, the page is blank | FEED DATA
Events | No feedback possible, the page is blank | No feedback possible, the page is blank | FEED DATA
Log in | Because of challenges in sign up, I am unable to log in
Giving | It does lead to an option page | Can the giving page have some more explanation on projects being supported and not just asking for money | 2022-05-02
Can we increase the number of ways to give to include M-Pesa